## Pending Work
DAM PreSchool — Pending Work (generated 2026-06-16, reconciled with code)
# | Area | Item | Status | Priority | Source | Notes / Next step
1 | Communication | Parent announcements view | Needs verification | High | app/(parent)/index.tsx (implemented this session) | DONE: 'Notices' button now opens a modal that fetches from announcements (audience-filtered) and shows title/body/attachment/date. Verify on device. Realtime live-update is the remaining follow-up (needs Realtime enabled on the table).
2 | Communication | Realtime announcements (live update) | Pending | Medium | follow-up to parent announcements view | Notices refetch each time the modal opens. Optional: subscribe via supabase.channel(postgres_changes) so new notices appear without reopening; requires enabling Realtime on the announcements table in Supabase.
3 | Communication | Parent–Teacher chat | Pending | High | PROGRESS_TRACKING.md | Messaging UI exists for admin; parent<->teacher channel not connected.
4 | Communication | Unread message indicators | Pending | Medium | README_DASHBOARDS.md | No unread badges on conversations.
5 | Communication | File attachments in messages/announcements | Pending | Low | README_DASHBOARDS.md | No file sharing support yet.
6 | Fees | Online fee payment integration | Pending | High | PROGRESS_TRACKING.md | Fees are view-only; no payment gateway wired.
7 | Fees | Admin fee collection / processing | Pending | High | PROGRESS_TRACKING.md | No way to record/collect payments from admin side.
8 | Fees | Payment receipt PDF download | Pending | Medium | docs/PAYMENT_RECEIPT_FEATURE.md | Receipt screen exists; 'Download PDF' marked coming soon.
9 | Appointments | Reschedule request backend | Pending | High | .kiro/specs/parent-appointment-modals (task 8.8) | Reschedule details only logged; replace with real backend call.
10 | Appointments | Update appointment in backend on reschedule | Pending | High | .kiro/specs/.../design.md (TODO) | Backend mutation not implemented.
11 | Admin | Class assignment (assign teachers to classes) | Pending | Medium | PROGRESS_TRACKING.md | Admin cannot assign teachers to classes.
12 | Admin | Holiday management (create/delete) | Needs verification | Medium | PROGRESS_TRACKING.md vs schema | Doc says view-only; holidays table + RLS exist — confirm admin CRUD UI.
13 | Admin | Reports analytics / charts | Pending | Medium | PROGRESS_TRACKING.md | Reports screen present; charts not connected to data.
14 | Admin | Admin profile editing | Pending | Low | app/(dashboard)/admin-profile.tsx:169 | 'Coming Soon' alert on edit profile.
15 | Admin | 'More' menu unrouted items | Pending | Low | app/(dashboard)/more.tsx:163 | Menu items without a route show 'Coming Soon'.
16 | Teacher | Teacher student list from DB | Needs verification | Medium | PROGRESS_TRACKING.md | Doc says not fetched from DB; verify against current teacher screens.
17 | Routing | Principal routes to admin dashboard | Needs verification | High | PROGRESS_TRACKING.md (known issue) | Doc flags principal landing on admin dashboard; verify auth-routing.ts handles principal.
18 | Notifications | Push notifications end-to-end | Needs verification | High | code: usePushNotifications.ts / send-push | IMPLEMENTED since the doc was written. Verify delivery on a physical prod build via adb logcat.
19 | Auth | Google OAuth PKCE fix | Needs verification | High | lib/supabase.ts / context/auth.tsx (this session) | flowType:pkce + Linking.createURL added. Rebuild APK and confirm sign-in completes.
20 | Infra | Consolidate SQL scripts into migrations | Pending | Medium | supabase/*.sql | Dozens of ad-hoc fix_/debug_ scripts; no versioned migrations folder.
21 | Infra | Error tracking service (Sentry/Bugsnag) | Pending | Low | utils/errorHandler.ts:146 | TODO: send errors to a tracking service.
22 | Quality | Offline support / caching | Pending | Low | README_DASHBOARDS.md | No offline caching for data fetches.
23 | Quality | Export reports (PDF/Excel) | Pending | Low | README_DASHBOARDS.md | Report export not implemented.